# AWS First Cloud AI Journey – Project Plan

# Team Super Beast Warrior – FPT University – Batch-Based Clickstream Analysis Platform

# [Date]

- Table of Contents

1	BACKGROUND and motivation	4

1.1	executive summary	4

1.2	PROJECT SUCCESS CRITERIA	4

1.3	Assumptions	4

2	SOLUTION ARCHITECTURE / ARCHITECTURAL DIAGRAM	5

2.1	Technical Architecture Diagram	5

2.1.1	Network Infrastructure	5

2.1.2	Data and Process Flow	5

2.1.3	Software Services and Components	5

2.1.4	Integration and Security Controls	6

2.1.5	Architecture Diagram	6

2.2	Technical Plan	6

2.3	Project Plan	6

2.4	Security Considerations	6

3	Activities AND Deliverables	7

3.1	Scope of Work	7

3.2	Deliverables	10

3.2.1	AWS Infrastructure (manual deployment)	10

3.2.2	Clickstream Ingestion	10

3.2.3	ETL Pipeline	10

3.2.4	Analytics Dashboard	11

3.2.5	Security & Monitoring	11

3.2.6	Documentation & Handover	11

3.3	Roles & Responsibilities	11

3.3.1	Partner (Mentor / Technical Team)	11

3.3.2	Student / Intern	11

3.3.3	Customer (Business Unit)	11

3.4	Risks & Mitigation	12

3.5	Success Criteria	12

4	EXPECTED AWS COST BREAKDOWN BY SERVICES	12

4.1	Amazon API Gateway	12

4.2	Amazon Cognito	12

4.3	Amazon IAM	13

4.4	Amazon CloudWatch	13

4.5	Amazon SNS	13

4.6	Amazon S3	13

4.7	Amazon EC2	13

4.8	Amazon CloudFront	13

4.9	Amazon Amplify	13

4.10	Amazon Lambda	13

4.11	Amazon Event Bridge	13

5	TEAM	13

6	resources & cost estimates	14

7	Acceptance	15

# BACKGROUND and motivation

## executive summary

Customer Background

The customer is an e-commerce business specializing in computer and peripheral product sales. As user traffic increases, the organization requires a centralized analytics platform to understand customer behavior, product engagement in order to support data-driven decision-making.

Business and Technical Objectives

- Implement a scalable and automated clickstream analytics platform on AWS.

- Collect user interaction events and process them in hourly batches.

- Deliver interactive dashboards for business insights and product performance analysis.

- Improve website performance and user experience using CloudFront and Amplify.

- Enhance security, governance, and auditing through IAM, Cognito, CloudWatch.

Use Cases

- Capture clickstream events (clicks, views, searches, add-to-cart).

- Store raw interaction data in Amazon S3.

- Process hourly ETL jobs using AWS Lambda and Event Bridge.

- Load curated datasets into a Data Warehouse hosted on Amazon EC2.

- Visualize operational and analytical metrics through an R Shiny dashboard.

- Host the website frontend on AWS Amplify with integrated CloudFront CDN.

- Provide secure authentication via Amazon Cognito.

Summary of Partner Services

The partner team will design and deploy the AWS architecture, build data ingestion and ETL pipelines, configure the Data Warehouse and R Shiny Server, implement security and monitoring components, and deliver full documentation and knowledge transfer to the customer’s technical staff.

## PROJECT SUCCESS CRITERIA

- Reliable clickstream data ingestion
≥ 95% of user interaction events (click, view, search, add-to-cart) are captured from the frontend and stored in Amazon S3 using the defined log schema.

- Automated batch processing (ETL)
The ETL pipeline is triggered every 60 minutes through Amazon EventBridge and completes batch execution within ≤ 5 minutes without major processing failures.

- Data pipeline efficiency
Total processing time from Raw Layer → Processed Layer → Data Warehouse is ≤ 10 minutes after each hourly batch schedule.

- Interactive analytics dashboard
The R Shiny dashboard displays at least five key business KPIs:

- Product popularity by item and category

- Sales funnel (view → add-to-cart → checkout → purchase)

- Traffic trends over time (hourly/daily)

- Session duration and bounce rate

- Customer interest by category/product

- Secure and stable AWS infrastructure
No public access to EC2 instances hosting the Data Warehouse and R Shiny services. IAM follows least-privilege access. CloudWatch logs and metrics are enabled for monitoring and troubleshooting.

- Low and predictable operating cost
The platform demonstration environment operates at ≤ 15 USD/month according to the AWS cost estimation table.

- Complete documentation and knowledge transfer
Architecture documentation, runbook, and operational guide are delivered to enable the customer team to operate and extend the system independently after project handover.

## Assumptions

- AWS environment readiness
A functional AWS account with sufficient permissions (VPC access, IAM configuration, S3, Lambda, EC2) is provided in Week 1 to ensure smooth deployment.

- Availability of clickstream data
Real or simulated clickstream event data is available to support end-to-end testing of ingestion, ETL pipeline, and dashboard analysis.

- No dependency on on-premise systems
The solution runs entirely on AWS Cloud without integration to on-premise databases, mainframe systems, or existing messaging buses.

- Data Warehouse hosted on EC2
To optimize costs for the demonstration, the Data Warehouse is implemented on Amazon EC2 instead of a fully managed Data Warehouse service like Redshift Serverless.

- Limited data volume for project scope
The data volume remains at demonstration scale and does not require full production optimization, horizontal scaling, or advanced performance tuning.

- Dashboard intended for demonstration purposes
The R Shiny dashboard is designed for demo and training usage, without advanced multi-tenant features, role-based access control, or SSO requirements.

- Customer participation in Agile timeline
The customer provides feedback during Sprint Reviews (every two weeks) to avoid delays in delivery and acceptance.

- Recognized potential risks

- Delays in IAM/VPC approval may impact deployment timelines

- Intern team may require additional support from mentors due to multi-service architecture

- Installation or configuration issues may occur while deploying R Shiny and database services on EC2 Linux

# SOLUTION ARCHITECTURE / ARCHITECTURAL DIAGRAM

## Technical Architecture Diagram

### Network Infrastructure

The environment is deployed inside an Amazon Virtual Private Cloud (VPC) consisting of:

- Public Layer

  - AWS Amplify Hosting for the e-commerce frontend, integrated with Amazon CloudFront as the global CDN.

  - API Gateway for handling ingest traffic from the frontend.

- Private Subnet 1 – OLTP Layer

  - EC2 instance hosting the operational transactional database for the e-commerce website.

- Private Subnet 2 – Analytics Layer

  - EC2 instance hosting the Data Warehouse.

  - EC2 instance hosting the R Shiny Server for dashboard visualizations.

- VPC Gateway Endpoint for Amazon S3

  - Ensuring private connectivity from Lambda and EC2 to S3 without requiring a NAT Gateway.

### Data and Process Flow

The system processes clickstream data through the following workflow:

- User Interaction

- Users access the website through Amplify + CloudFront, which delivers static web assets with low latency.

- Event Collection

- A JavaScript SDK embedded in the frontend sends user interaction events (clicks, views, searches) to Amazon API Gateway.

- Ingestion Layer

- API Gateway invokes an AWS Lambda function that validates and stores raw clickstream data into Amazon S3 (Raw Layer).

- Batch Processing (ETL)

- Amazon Event Bridge triggers the ETL Lambda function every 60 minutes.

- The Lambda function reads raw logs from S3, performs cleaning, transformation, and normalization.

- Processed data is written to S3 Processed Layer and loaded into the EC2 Data Warehouse.

- Analytics & Visualization

- An R Shiny Server on EC2 queries the Data Warehouse to provide dashboards displaying product popularity, customer behavior, sales funnels, and traffic trends.

### Software Services and Components

The architecture includes the following AWS services:

- Frontend & Delivery: AWS Amplify, Amazon CloudFront

- Data Ingestion: Amazon API Gateway, AWS Lambda

- Storage: Amazon S3 (Media Assets, Raw Data, Processed Data)

- ETL & Scheduling: AWS Lambda, Amazon Event Bridge

- Compute (Analytics): Amazon EC2 (Data Warehouse, R Shiny Server)

- Security & Access Control: Amazon Cognito, AWS Identity and Access Management (IAM)

- Monitoring & Logging: Amazon CloudWatch, Amazon SNS

- Networking: VPC, Subnets, S3 VPC Endpoint, Security Groups

### Integration and Security Controls

- Authentication & Authorization: Amazon Cognito manages secure user sign-in and token-based access to APIs.

- Least-privilege IAM Policies are enforced for Lambda, API Gateway, EC2, and S3 access.

- Operational Metrics & Alerts are configured in Amazon CloudWatch and forwarded to Amazon SNS.

- Private subnets ensure no direct public access to the Data Warehouse or Shiny workloads.

- S3 VPC Endpoint ensures internal-only communication without exposing resources to the internet.

### Architecture Diagram

## Technical Plan

[Partner] will deploy all required AWS resources manually following AWS best practices. The team will configure each service from scratch to ensure the Batch-based Clickstream Analytics Platform is built accurately, securely, and aligned with the customer’s requirements.

Some additional configurations—such as IAM permission boundaries, VPC security rules, S3 VPC Endpoints, and database access policies—may require prior approval from the customer’s governance and security teams. These items will follow the customer’s defined security review and change-management processes to ensure alignment with organizational standards.

All critical technical components will be validated through extensive test coverage, including the S3 ingestion process, Event Bridge 60-minute scheduling, Lambda-based ETL workflows, and data loading into the EC2-hosted data warehouse. Please refer to Appendix X for the detailed test cases covering functional validation, error handling, and end-to-end pipeline execution.

## Project Plan

The development team will follow an accelerated Agile approach over a 6-week delivery timeline, structured into three (3) two-week sprints. Throughout the project, the team will conduct Sprint Reviews to present progress and gather direct feedback from the customer.

The development team will be responsible for all activities, including infrastructure setup, data ingestion workflows, ETL processing, data warehouse integration, and dashboard preparation. The customer’s role will focus on providing requirements, reviewing deliverables during sprint reviews, and validating the final output.

Communication cadences will consist of daily stand-ups within the development team and bi-weekly sprint reviews with the customer to ensure transparency and alignment.

Knowledge transfer sessions will focus on delivering the final product to the customer at the end of the final sprint, guiding them through system usage, and demonstrating the visualization dashboards so that they can operate the platform confidently after handover.

## Security Considerations

[Partner] will incorporate security controls across all layers of the solution. Identity access will be governed through MFA, scoped IAM roles, and controlled connectivity to the EC2 data warehouse. The underlying infrastructure will operate within private subnets and leverage an S3 VPC Endpoint to avoid exposure to the public internet. Data stored in S3 will be encrypted, while all service-to-service communication will use secure channels. CloudWatch monitoring will track pipeline health and surface operational irregularities. [Customer] will outline their compliance expectations so that all implemented safeguards align with internal standards.

# Activities AND Deliverables

## Scope of Work

The project aims to build a user behavior analytics platform (clickstream analytics) for an e-commerce website as part of the AWS internship reporting requirements.

The system includes the following main components:

- User Behavior Data Collection (Clickstream Ingestion)

Track key events on the website:

- Click on product, add to cart, purchase

- Product detail views, category views

Track user sessions:

- Time entering/exiting the website

- Device and browser (basic level)

Track user journey:

- Sequence of visited pages (pageview sequence)

Frontend data is sent to API Gateway → Lambda → S3 (Raw Layer).

- Data Processing Pipeline (ETL – Batch)

Executed every 60 minutes using Event Bridge.

Data cleaning and normalization:

- Remove invalid records / missing required fields

- Normalize timestamp, user/session ID, event type

Store processed data into S3 Processed Layer.

Load data from Processed Layer into the Data Warehouse (PostgreSQL/Redshift on EC2) for analytics.

- Analytics Dashboard (R Shiny Dashboard)

Build an R Shiny dashboard hosted on EC2.

Connect to Data Warehouse to display:

- Customer interest by product/category

- Product popularity (click counts)

- Sales funnel (view → add to cart → checkout → purchase)

- Onsite time, bounce rate, session duration

- Traffic over time (hourly, daily)

- Supporting AWS Infrastructure

Frontend: AWS Amplify + CloudFront (hosting + CDN for the demo e-commerce website).

Compute & Data:

- EC2 for OLTP Database (demo transactional database)

- EC2 for Data Warehouse + R Shiny Server

Security & Monitoring:

- IAM: least privilege access

- Cognito: user authentication (if login is required)

- CloudWatch: logs, metrics

- SNS: notifications when pipeline fails (optional demo)

Project scope guarantees a full clickstream flow:
User → Website → AWS → ETL → Data Warehouse → Dashboard for business insights.

| Project Phase | Timeline | Activities | Milestones | Total man-day |
| --- | --- | --- | --- | --- |
| Topic Selection & AWS Service Research | Week 1 | Study business requirements: why enterprises need clickstream analytics Research examples / best practices Official topic selection: “Building a user behavior analytics system (clickstream analytics) for an e-commerce website on AWS.” Study services to be used: - S3, EC2, Lambda, API Gateway, Event Bridge - VPC, IAM, CloudFront, Amplify, CloudWatch, SNS, Cognito Write the proposal: - Project objectives - Scope - AWS service list - Business benefits and internship value | - Topic approved - Draft service list - Proposal completed | [X man-day] |
| Architecture Design | Week 2 | - Analyze how AWS services work together for clickstream analytics - Finalize AWS service list - Design diagrams: High-level architecture: - Frontend (Amplify + CloudFront) - API Gateway → Lambda → S3 (Raw/Processed) - ETL → Data Warehouse (EC2) - R Shiny Dashboard (EC2) Write architectural descriptions: - Role of each service - Reason for choosing the service Plan detailed tasks for Weeks 3–6. | - Architecture diagrams finished - Final AWS service list - Architectural description drafted | [X man-day] |
| Build Application & Local Pipeline | Week 3 | Initialize project source code (frontend + backend) locally: - Frontend: main pages (home, product list, product detail, cart…) with mock data - Backend: simple local API to simulate logging Integrate clickstream tracking on frontend: - Send events to local API on click/view/search Local clickstream pipeline: Web → Backend collector → local file/log → temporary processing script End-to-end testing on local. | - Web demo + backend collector running locally - Local clickstream logging working | [X man-day] |
| Stabilize Local System | Week 4 | Optimize tracking: - Avoid duplicate logs, ensure key events captured - Standardize log format (JSON schema, field names, timestamp) Build local processing (mini-ETL): - Clean data (remove missing IDs, invalid events) - Simple aggregation (e.g., view count per product) Fix bugs, improve basic performance: - Prevent excessive logging that slows UI Deliver “local stable version” – foundation for AWS deployment. | - Stable local pipeline - Local version ready for cloud deployment | [X man-day] |
| Deploy on AWS (Cloud Deployment) | Week 5 | Set up AWS infrastructure: - VPC, Subnets, Security Groups - S3 buckets: Raw Layer, Processed Layer - IAM roles/policies - Event Bridge, API Gateway, Lambda Deploy: - API Gateway for receiving events - Lambda ingestion → S3 Raw - Amplify/CloudFront → host frontend Connect frontend → API Gateway → Lambda → S3 Replace local endpoints with AWS endpoints. Cloud end-to-end test. Basic CloudWatch: - Lambda logs - Basic error/event metrics | - AWS infrastructure deployed - Clickstream ingestion working on AWS (events → S3 Raw) | [X man-day] |
| ETL, Dashboard & Final Report | Week 6 | Event Bridge rule: trigger every 60 minutes. Lambda ETL: - Read from Raw - Clean & normalize - Write into Processed Layer or insert into Data Warehouse Set up EC2: - EC2 for Data Warehouse (PostgreSQL/Redshift / PostgreSQL on EC2) - EC2 for R Shiny Server Build R Shiny Dashboard: - User behavior overview - Product view tracking - Conversion funnel - Session duration & bounce rate - Traffic over time Final end-to-end test on AWS. Finalize: - Architecture documentation - Operations manual (runbook) - Final report + presentation | - ETL batch working - Data Warehouse populated - R Shiny Dashboard running - Documentation & final presentation completed | [X man-day] |

## Deliverables

### AWS Infrastructure (manual deployment)

Includes:

- VPC, Subnets, Security Groups

- S3: Raw Layer, Processed Layer

- API Gateway, Lambda, Event Bridge

- EC2 for:

  - OLTP Database

  - Data Warehouse

  - R Shiny Server

- Amplify/CloudFront for frontend deployment

### Clickstream Ingestion

- API Gateway endpoint

- Lambda ingestion function

- Log schema + validation rules

### ETL Pipeline

- Event Bridge schedule (every 60 minutes)

- Lambda ETL:

  - Read Raw

  - Clean / normalize

  - Write Processed / Load DW

- SQL/script for DW loading

### Analytics Dashboard

R Shiny dashboard on EC2:

- User behavior overview

- Product view/click tracking

- Conversion funnel

- Session duration & bounce rate

- Time-series traffic analytics

### Security & Monitoring

- IAM least privilege policies

- CloudWatch logs & metrics

- SNS notifications (optional)

### Documentation & Handover

- Architecture document

- Runbook (operations guide)

- IaC deployment document

- Internship report + presentation slides

## Roles & Responsibilities

### Partner (Mentor / Technical Team)

- Provide AWS architectural guidelines

- Support service selection

- Review design/code; assist debugging

- Evaluate final result

### Student / Intern

- Analyze requirements & propose solution

- Design architecture + diagrams

- Develop all pipelines: ingestion, ETL, DW, dashboard

- Write documentation & final report

### Customer (Business Unit)

- Provide business requirements

- Provide sample datasets (if any)

- Review key milestones (M2, M4, M6)

- Approve final deliverables

## Risks & Mitigation

| Risk | Level | Mitigation |
| --- | --- | --- |
| Limited 6-week duration, many AWS services to learn | High | Prioritize core features, reduce optional parts |
| Delays in AWS account/IAM/VPC approval | High | Request resources in Week 1 and follow up frequently |
| Large clickstream data slows ETL | Medium | Use S3 partitioning; limit data scope for demo |
| Difficulty installing R Shiny & DB on EC2 | Medium | Do small PoC first; follow official docs |
| Additional dashboard requirements outside initial scope | Low | Lock scope in Week 2; document clearly |

## Success Criteria

Clickstream ingestion works reliably locally and on AWS

Raw → Processed → DW data flows correctly

ETL batch runs every 60 minutes without major errors

R Shiny dashboard reads from DW and displays:

- Product view/click metrics

- Basic funnel

- Traffic over time

AWS infrastructure includes logging and monitoring sufficient for debugging

Final report + slides clearly describe:

- Architecture

- Reason for choosing AWS services

- End-to-end data flow

- Demo results

# EXPECTED AWS COST BREAKDOWN BY SERVICES

## Amazon API Gateway

- HTTP API requests units (thousands), Average size of each request (34 KB), REST API request units (millions), Cache memory size (GB) (None), WebSocket message units (thousands), Average message size (32 KB), Requests (10 per month) 0.01 USD/monthly

## Amazon Cognito

- User Pools: 0.10 USD/monthly

## Amazon IAM

- IAM has no direct cost; only used for access control, user roles, and service permissions

## Amazon CloudWatch

- GetMetricData: Number of metrics requested (100), GetMetricWidgetImage: Number of metrics requested (1000), Number of other API requests (1000) 0.03 USD/monthly

## Amazon SNS

- Requests (1000000 per month), EMAIL/EMAIL-JSON Notifications (1000 per month), HTTP/HTTPS Notifications (100000 per month), SQS Notifications (100000000 per month), Amazon Web Services Lambda (100000000 per month), Amazon Kinesis Data Firehose (100000 per month) 0.03 USD/monthly

## Amazon S3

- PUT, COPY, POST, LIST requests to S3 Standard (1000), GET, SELECT, and all other requests from S3 Standard (1000), Data returned by S3 Select (6 GB per month), Data scanned by S3 Select (6 GB per month), S3 Standard storage (6 GB per month) DT Inbound: Internet (6 TB per month) 0.18 USD/monthly

## Amazon EC2

- Tenancy (Shared Instances), Operating system (Linux), Workload (Consistent, Number of instances: 1), Advance EC2 instance (t3.small), Pricing strategy (Compute Savings Plans 3yr No Upfront), Enable monitoring (disabled), DT Inbound: Not selected (0 TB per month), DT Outbound: Not selected (0 TB per month), DT Intra-Region: (0 TB per month) 9.42 USD/monthly

## Amazon CloudFront

- Data transfer out to internet (6 GB per month), Data transfer out to origin (6 GB per month), Number of requests (HTTPS) (6 per month), Number of requests (HTTPS) ( per month) 1.08 USD/monthly

## Amazon Amplify

- Select build instance size (Standard (8 GB Memory, 4 vCPUs)), Duration of each request (in ms) (500), Number of build minutes (1 per month), Data stored per month (1 GB), Data served per month (1 GB), Number of SSR requests (1 per hour) 0.20 USD/monthly

## Amazon Lambda

- Service settings: 1.000.000 requests free 0.0 USD/monthly

## Amazon Event Bridge

- Event Bridge Event Bus - Ingestion: Number of AWS management events 1.000.000 events is free 0.0 USD/monthly

Total with monthly is 11.05 USD/monthly

Total with 1 year is 132.60 USD/12 monthly

# TEAM

Partner Executive Sponsor

| Name | Title | Description | Email / Contact Info |
| --- | --- | --- | --- |
| Trieu Quoc Hao | Executive Sponsor | Lead, Partner Data & Analytics Delivery Office | regit3108@gmail.com |

Project Stakeholders

| Name | Title | Stakeholder for | Email / Contact Info |
| --- | --- | --- | --- |
| Jane Smith | Director, E-Commerce | Digital Commerce Business Unit | smith@gmail.com |
| Ivan Doctorow | Sr. Manager, QA | IT – Testing & Quality Assurance | ivand@gmail.com |
| Dan Jacobs | VP, IT Operations | IT Operations – Infrastructure & Networking | danj@gmail.com |
| Emily | Data Governance Lead | Enterprise Data Governance Office | emily@gmail.com |

Partner Project Team

| Name | Title | Role | Email / Contact Info |
| --- | --- | --- | --- |
| Trieu Quoc Hao | Delivery Manager | Project Manager & Lead of Data Analytics | regit3108@gmail.com |
| Nguyen Van Duy Khiem | Solutions Architect | Technical Lead | khiemnguyen120216@gmail.com |
| Hoang Van Anh | Cloud Cost & Infrastructure Specialist | Infrastructure Lead | Anhhvse180142@fpt.edu.vn |
| Mai Nhat Thong | Data Engineer (ETL & Pipeline) | ETL & Data Pipeline Lead | maithongnhat1124@gmail.com |
| Tran Tin | Frontend Integration Engineer | Frontend Integration Lead | hoangtin0406@gmail.com |

Project Escalation Contacts

| Name | Title | Role | Email / Contact Info |
| --- | --- | --- | --- |
| Trieu Quoc Hao | Delivery Manager | Project Manager | regit3108@gmail.com |
| Nguyen Van Duy Khiem | Solutions Architect | Technical Lead | khiemnguyen120216@gmail.com |
| Mai Nhat Thong | Data Engineer (ETL & Pipeline) | ETL & Data Pipeline Lead | maithongnhat1124@gmail.com |

# resources & cost estimates

| Resource | Responsibility | Rate (USD) / Hour |
| --- | --- | --- |
| Solution Architect (1 HC) | Designs AWS solutions, VPC architecture, security, ingestion pipeline, ETL pipeline, Data Warehouse, and Shiny Server | 35 USD/hour |
| Data Engineer (1 HC) | Develops ingestion Lambda, designs S3 Raw/Processed layers, builds the 60-minute ETL batch pipeline, and performs data optimization | 32 USD/hour |
| Cloud Cost & Infrastructure Specialist (1 HC) | Estimates and optimizes AWS service costs; designs infrastructure (VPC, IAM, Endpoints); supports infrastructure validation and testing | 32 USD/hour |
| Full-stack / Frontend Engineer (1 HC) | Integrates the clickstream SDK into the Amplify frontend and performs event validation | 32 USD/hour |
| Other – BA / PM (Optional) | Gathers business requirements, manages the project timeline, organizes sprint reviews, and communicates with stakeholders | 30 USD/hour |

* Note: Refer to section “activities & deliverables” for the list of project phases

| Project Phase | Solution Architects | Engineers | Other (Please specify) | Total Hours |
| --- | --- | --- | --- | --- |
| Week 1 – Infrastructure Setup | 12 hour | 6 hour | 16 hour (Cloud 10 + PM 6) | 34 hour |
| Week 2 – Ingestion Pipeline | 6 hour | 22 hour | 4 hour (PM 4) | 32 hour |
| Week 3 – ETL + Data Warehouse | 8 hour | 20 hour | 4 hour (Cloud 4) | 32 hour |
| Week 4 – Dashboard + E2E Testing | 6 hour | 16 hour | 8 hour (Cloud 2 + PM 6) | 30 hour |
| Total Hours | 32 hour | 64 hour | 32 hour | 128 hour |
| Total Cost | 1000 USD | 1,556 USD | 723 USD | 3,288 USD |

Cost Contribution distribution between Partner, Customer, AWS:

| Party | Contribution (USD) | % Contribution of Total |
| --- | --- | --- |
| Customer | 3,288.52 | 100% |
| Partner | 0 | 0% |
| AWS | 0 | 0% |

# Acceptance

Upon completion of the project, the team will deliver the fully functional Batch-based Clickstream Analytics Platform to the Customer, including the processed datasets, configured AWS services, and visualization dashboards. A final product demonstration will be conducted so the Customer can review all features, validate the data pipeline behavior, and assess dashboard outputs.

The Customer will have five business days to evaluate the delivered system and confirm that it meets the agreed project objectives. If the platform operates as expected, the Customer will provide written acceptance confirmation.

If any issues or missing functionalities are identified, the Customer will provide written feedback specifying the areas requiring adjustment. The team will address the reported issues and resubmit the updated deliverable for re-evaluation. The Customer’s review for the resubmission will be limited to the corrected items.

If no feedback or rejection notice is provided within the evaluation period, the platform will be deemed accepted.